## PRE-FEST
ACDA 2017 Central Technical Schedule v1		Updated:
SUBJECT TO CHANGE		02/08/2017
	SATURDAY – MARCH 25th, 2017
TIME	WILNER THEATRE	NOTES
9:00-1:00	Fit Up / Hang Lighting and Sound
1:00-2:00	LUNCH	LUNCH
2:00-5:00	Fit Up / Hang Lighting and Sound

	SUNDAY – MARCH 26th, 2017
1:00-5:00	Focus Lighting
5:00-TBA	Troubleshooting - Ben Roose and Nick Smith Only (if required)

	MONDAY / TUESDAY - MARCH 27th / 28th, 2017
9:30-11:00	WSU Dancers to Lay Dance Floor (Monday)
Mon-Tues	Ben and Nick to Troubleshoot and Clean Up Prior to Festival

	END OF PRE-FESTIVAL FIT UP

## WEDNESDAY
ACDA 2017 Central Technical Schedule v1		Updated:
SUBJECT TO CHANGE		02/08/2017
	WEDNESDAY – MARCH 29th, 2017
TIME	WILNER THEATRE (Technical Rehearsals/Concerts)	NOTES
9:00-11:00	Tech Time if Required (CREW ONLY)
11:00-11:20
11:20-11:40
11:40-12:00
12:00-12:20
12:20-12:30	Buffer/Break	Buffer/Break
12:30-12:50
12:50-1:10
1:10-2:10	LUNCH	LUNCH
2:10-2:30
2:30-2:50
2:50-3:10
3:10-3:30
3:30-3:40	Buffer/Break	Buffer/Break
3:40-4:00
4:00-4:20
4:20-4:40	Technical Reset (CREW ONLY)
4:40-5:50	DINNER	DINNER
5:50-6:30	B/O Check / → House Open
6:30-9:15	ADJUDCATION CONCERT 1
9:15-9:30	Buffer/Break	Buffer/Break
9:30-10:45	ADJUDCATION FEEDBACK 1
10:45 PM	END OF DAY	END OF DAY

## THURSDAY
ACDA 2017 Central Technical Schedule v1		Updated:
SUBJECT TO CHANGE		02/08/2017
	THURSDAY – MARCH 30th, 2017
TIME	WILNER THEATRE (Technical Rehearsals/Concerts)	NOTES
7:00-7:30	Technical Reset (CREW ONLY) - If Required
7:30-7:50
7:50-8:10
8:10-8:30
8:30-8:50
8:50-9:00	Buffer/Break	Buffer/Break
9:00-9:20
9:20-9:40
9:40-10:00
10:00-10:20
10:20-10:30	Buffer/Break	Buffer/Break
10:30-10:50
10:50-11:10
11:10-11:30	Technical Reset (CREW ONLY)
11:30-12:00	LUNCH	LUNCH
12:00-12:30	B/O Check / → House Open
12:30-2:30	ADJUDCATION CONCERT 2
2:30-2:50	Buffer/Break	Buffer/Break
2:50-3:10
3:10-3:30
3:30-3:50
3:50-4:10
4:10-4:20	Buffer/Break	Buffer/Break
4:20-4:40
4:40-5:00
5:00-5:20
5:20-5:40
5:40-6:00	Technical Reset (CREW ONLY)
6:00-7:00	Buffer/DINNER	Buffer/DINNER
7:00-7:30	B/O Check / → House Open
7:30-9:15	ADJUDCATION CONCERT 3
9:15-9:30	Buffer/Break	Buffer/Break
9:30-10:45	ADJUDCATION FEEDBACK 3
10:45 PM	END OF DAY	END OF DAY

## FRIDAY
ACDA 2017 Central Technical Schedule v1		Updated:
SUBJECT TO CHANGE		02/08/2017
	FRIDAY – MARCH 31st, 2017
TIME	WILNER THEATRE (Technical Rehearsals/Concerts)	NOTES
7:00-7:30	Technical Reset (CREW ONLY) - If Required
11:00-11:20
11:20-11:40
11:40-12:00
12:00-12:20
12:20-12:30	Buffer/Break	Buffer/Break
12:30-12:50
12:50-1:10
1:10-2:10	LUNCH	LUNCH
2:10-2:30
2:30-2:50
2:50-3:10
3:10-3:30
3:30-3:40	Buffer/Break	Buffer/Break
3:40-4:00
4:00-4:20
4:20-4:40	Technical Reset (CREW ONLY)
4:40-5:50	DINNER	DINNER
5:50-6:30	B/O Check / → House Open
5:30-8:00	ADJUDCATION CONCERT 4
8:00-8:15	Buffer/Break	Buffer/Break
8:15-9:45	ADJUDCATION FEEDBACK 4
09:45 PM	END OF DAY	END OF DAY

## SATURDAY
ACDA 2017 Central Technical Schedule v1		Updated:
SUBJECT TO CHANGE		02/08/2017
	SATURDAY – APRIL 1st, 2017
TIME	WILNER THEATRE (Technical Rehearsals/Concerts)	NOTES
10:00-11:00	Technical Reset (CREW ONLY) - If Required
11:00-11:20
11:20-11:40
11:40-12:00
12:00-12:20
12:20-12:30	Buffer/Break	Buffer/Break
12:30-12:50
12:50-1:10
1:10-2:10	LUNCH	LUNCH
2:10-2:30
2:30-2:50
2:50-3:10
3:10-3:30
3:30-3:40	Buffer/Break	Buffer/Break
3:40-4:00
4:00-4:20
4:20-4:40	Technical Reset (CREW ONLY)
4:40-6:30	DINNER	DINNER
6:30-7:00	B/O Check / → House Open
7:00-9:45	GALA CONCERT
9:45-10:00	Buffer/Break	Buffer/Break
10:00 PM	GALA RECEPTION	GALA RECEPTION

	SUNDAY – APRIL 2nd, 2017
1:00-5:00	Strike (Crew and WSU Dancers)
5:00 PM	END OF ACDA 2017 CONFERENCE